## Slide 1: Section 1 : Project monitoring and evaluation

## Slide 2: Presentation contents
Overview of the Project and its cycle
Concepts of project monitoring and Evaluation
The why of project monitoring and evaluation
The difference and similarities between project monitoring and evaluation
Criteria to select good monitoring and evaluation tools

## Slide 3: Provocative Questions
What is a project? And why organizations show deep interest to design a project proposal ?
Does every task require project interventions?

## Slide 4: Project and its cycle
Originated - the Latin verb "Proiicers",
Meaning - "throw forward." - an introduction of proposal
Proposal – May introduce new ideas, improvements, and changes, are put forward.
A set of investments and other planned activities aimed at achieving specific objectives within a pre-determined timeframe and budget.
A project is also an activity carried out with a defined goal, during a definite period, with a pre-determined input of resources and using specific modes of work.

## Slide 5: Various types of projects
The following are major types of projects.
  Development projects
  Construction Projects
  Evaluation projects
  Education Projects
  Research Projects
  Study Projects etc.,
Which types of project are you often engaged in?

## Slide 6: To recapitulate,
A project is "a temporary endeavor undertaken to create a unique product or service.
Temporary means that every project has a definite end.
Unique means that the product or service is different in some distinguishing way from all similar products or services."

## Slide 7
Project Cycle: Summary Table
No | Magnen 1991 | Weiss and Wysocki (1992) | Westland (2006) | Nicholas (2001) | Lewis (2001)
1 | Identification | Define | Initiation | Defining | Definition
2 | Preparation | Plan | Planning | Planning | Planning strategy
3 | Appraisal | Organize | Execution | Executing | Implementation planning
4 | Negotiation | Control | Closure | Delivering | Execution and control
5 | Implementation | Close |  |  | Lessons learned (closeout)
6 | Evaluation |  |  |  | 

## Slide 8: Concepts of Project Monitoring and Evaluation
…are a process of continually gathering information and assessing it to determine whether progress is being made towards pre-specified goals and objectives and to highlight any unintended (positive or negative) effects from a project and its activities
Anyone who can explain what they are?

## Slide 9: Specifically
Monitoring
  is carried out to track progress and performance as a basis for decision-making at various steps in an initiative or project process.
  can be carried out during the implementation of every activity.
  is an ongoing process.
Evaluation
  is a more generalized assessment of data or experience to establish to what extent the initiative has achieved its goals or objectives.
  is a systematic method for collecting, analyzing, and using the information to answer questions about projects, policies, programs, and so forth.

## Slide 10: The why of project monitoring and evaluation
Why do organizations engage in M&E?
Brainstorming

## Slide 11: Most common rationales
Addressing the issue of accountability:
demonstrating to donors, taxpayers, beneficiaries and implementing partners that expenditure, actions, and results are as agreed or can reasonably be expected in the situation.
For operational management:
provision of the information needed to coordinate the human, financial and physical resources committed to the project or program and to improve performance
For strategic management:
provision of information to inform setting and adjustment of objectives and strategies.
For capacity building:
building the capacity, self-reliance and confidence of beneficiaries and implementing staff and partners to initiate and implement development initiatives effectively.

## Slide 12: The differences and similarities between project monitoring and evaluation
The complementary nature of monitoring and evaluation
The difference between monitoring and evaluation

## Slide 13
Complementary Nature
Monitoring | Evaluation
Implementation oriented Tracks results Assess intermediate results Focus on timeliness Emphasis on multi-level results Informs budgeting Strengthens accountability for managing results Essential for program implementation & improvements Can use disaggregated data | Policy-oriented Explain results Assess attributes Focus on rigor Emphasis on final results Informs broad resources allocation Strengthens accountability for results themselves Essential for strategy development May need aggregated data

## Slide 14
Criteria | Monitoring | Evaluation
Objectives | To determine the efficiency & legitimacy of "the application and use of inputs as well as their conversion into outputs. To facilitate an adjustment of activity plans, time schedules or budgets. | To determine whether the objectives set were realistic given the capacities and circumstances in which they had to be fulfilled. To undertake a review of things done, i.e., to assess the impact of the project activities.
Reference Period Frequency | It takes place during the execution of a program project activity. A continuous feedback system remains in force throughout the program/project implementation stage. Focus on inputs process cut put and work plan | Carried out periodically, i.e., before the implementation of the program project and during different periods while the planned activities are in progress as well as after they become operational. Focus on effectiveness, relevance, impact and cost-effectiveness
Primary Users | It is a tool for project managers to use in judging and influencing the implementation progress. | Results are used by funding agencies and other relevant institutions in future program/project design
Data Gathered | Primarily quantitative | Primarily qualitative